**Pacific Judicial Strengthening Initiative (Phase II)**

**Indicative Activity Schedule - Chronological Order**

***June-December 2021***

*as at 3 September 2021*

| **Activity Type** | **Activity** | **Location** | **Tentative Timing** | **Project** |
| --- | --- | --- | --- | --- |
| **2021** |
| Remote (Local) | Sustainable Development Goals Webinar and Follow-up support | Palau, FSM, Kiribati | 10 Jun, 21 | SDG |
| Remote (Regional) | Webinar #1: Community Engagement Guidance Note Launch | Regional |  24 Jun, 21 | Localising Prof. Cap. Build. |
| Remote (Local) | Information, Communications and Technology remote support to scope Case Tracking-related needs Activity | Niue | Jun-Aug, 21 | Efficiency |
| Remote (Local) | Court Annual Reporting & Disaggregated Data support | Nauru | Jun-Aug, 21 | Accountability |
| Remote (Local) | Support to COJ materials for inclusion in secondary school curriculum #1 | Kiribati | Jun-Aug, 21 | Access to Justice |
| Remote (Local) | Support to COJ materials for inclusion in secondary school curriculum #2 | Vanuatu | Jul-Sept, 21 | Access to Justice |
| Remote (Local) | Support to COJ materials for inclusion in secondary school curriculum #3 | FSM | Jul-Sept, 21 | Access to Justice |
| Remote (Local) | Support to COJ materials for inclusion in secondary school curriculum #4 | RMI | Jul-Sept, 21 | Access to Justice |
| Remote (Local) | Support to COJ materials for inclusion in secondary school curriculum #5 | PNG | Jul-Sept, 21 | Access to Justice |
| Remote (Regional) | Webinar #2: Judicial Wellbeing in Pacific Partner Court Webinar | Regional | 29 Jul, 21 | Localising Prof. Cap. Build. |
| Remote (Local) | Court Annual Reporting & Disaggregated Data support | Tokelau | Aug-Sept, 21 | Accountability |
| Remote (Local) | Remote Court Proceedings Toolkit Pilot Follow-up | Tonga, Niue, Cook Islands, Solomon Islands | Sept-Oct, 2021 | Efficiency |
| Remote (Local) | Human Rights Checklists Pilot #1 | Vanuatu | 20-24 Sept, 21 | Human Rights |
| Remote (Local) | Remote Court Proceedings Toolkit Roll-out | TBC | Sept-Oct, 21 | Efficiency |
| Remote (Local) | Human Rights Checklists Pilot #2 | Samoa  | 5-7 Oct, 21 | Human Rights |
| Remote (Regional) | Webinar #3: Open Forum (TBC) | Regional | 14 Oct, 21 | Localising Prof. Cap. Build. |
| Remote (Regional)  | 8th Chief Justices’ Leadership Forum/MFAT Transition | Regional | 3 Nov, 21 | Regional Leadership |
| Remote (Regional) | 11th Initiative Executive Committee Meeting | Regional | 4 Nov, 21 | Regional Leadership |
| Remote (Regional) | Remote Delivery Facilitation #3 | Regional | Jun-Dec 21 | National Leadership  |

***Leadership Incentive Fund:***

| **Activity** | **Deadline** |
| --- | --- |
| *LIF Applications available for all PICs*  | *Round 4: LIF applications are available from June to September, 2021.* |