

**Pacific Judicial Support Initiative**

**Six-monthly**

**Progress Report**

***15 February 2017***

******

**FEDERAL COURT**

**OF AUSTRALIA**



*PJSI is funded by the New Zealand Government and*

*implemented by the Federal Court of Australia*

**Table of Contents**

[Abbreviations 3](#_Toc471997015)

[Executive Summary 4](#_Toc471997016)

[Top 3 highlights 4](#_Toc471997017)

[Summary of Progress 4](#_Toc471997018)

[1. Activity Summary 5](#_Toc471997019)

[2. Attributing Success 6](#_Toc471997021)

[3. Primary Changes 6](#_Toc471997022)

[4. Risks and Opportunities 6](#_Toc471997023)

[5. Changes 6](#_Toc471997024)

[6. Capacity Improvements 7](#_Toc471997025)

[7. Human Rights and Gender 7](#_Toc471997026)

[8. Sustainability 7](#_Toc471997027)

[9. Initiative Management 7](#_Toc471997028)

[10. Conclusion 9](#_Toc471997029)

[Annexures 10](#_Toc471997030)

[Annex A: 24-month Schedule of Activities 11](#_Toc471997031)

[Annex B: Results Diagram and Framework 12](#_Toc471997032)

[Annex C: Costed Workplan 24](#_Toc471997033)

[Annex D: Expenditure Summary (to 31 December, 2016) 25](#_Toc471997034)

## Abbreviations

|  |  |  |
| --- | --- | --- |
| ADD | - | Activity Design Document |
| CJ | - | Chief Justice |
| PCJE | - | PNG’s Centre for Judicial Excellence |
| CJLF#1 | - | First Chief Justices’ Leadership Forum |
| FCA | - | Federal Court of Australia |
| FSM | - | Federated States of Micronesia |
| GFV | - | Gender & Family Violence |
| IEC | - | Initiative Executive Committee |
| JLC | - | Judicial Liaison Committee |
| LIF | - | Leadership Incentive Fund |
| MFAT | - | New Zealand Ministry of Foreign Affairs and Trade |
| M&E | - | Monitoring and Evaluation |
| PIC | - | Pacific Island Country |
| PJSI | - | Pacific Judicial Strengthening Initiative |
| PNG | - | Papua New Guinea |
| USP |  | University of the South Pacific |

## Executive Summary

This report provides a summary of progress achieved during the mobilisation phase and the first six-months of the Pacific Judicial Strengthening Initiative (PJSI) during the period 24 May, 2016 - 31 January, 2017. The report is submitted in satisfaction of Milestone 3 defined in the grant funding agreement between the New Zealand Ministry of Foreign Affairs and Trade (MFAT) and the Federal Court of Australia (FCA).

## Highlights

1. Executive Committee approval of the PJSI design, activities, strategies and scheduling.
2. Development and launch of the Leadership Incentive Fund.
3. Successful delivery of inaugural leadership activities.

## Summary of Progress

PJSI is being successfully implemented on schedule and within budget. Four activities have taken place with several others having been designed, commenced and/or planned during the reporting period.

|  |  |
| --- | --- |
| **Activity** | **Progress** |
| **Output 1: Regional Leadership** | |
| *1st Chief Justices’ Leadership Forum & Initiative Executive Committee Meeting* | Complete |
| *2nd Chief Justices’ Leadership Forum & Initiative Executive Committee Meeting* | On track |
| **Output 2: National Leadership** | |
| *Project Management & Evaluation Workshop* | On track |
| **Output 3: Leadership Incentive Fund** | |
| *Development and approval of guidelines and launch of Fund* | Complete |
| **Output 7: Institutionalising Professional Development** | |
| *Career Pathway: preliminary assessment completed and approved by stakeholders; local visits #1 and #2 undertaken* | On track |
| *Career Gateway: preliminary assessment completed and approved by stakeholders; local visit #1 undertaken* | On track |
| **Output 8: Human Rights** | |
| *Strategy completed and Toolkit drafting commenced* | On track |
| **Output 9: Gender & Family Violence** | |
| *Strategy completed, Local Expert contracted and Toolkit drafting commenced* | On track |
| **Output 11: Accountability** | |
| *Strategy completed and implementation of work plan has begun* | On track |
| *M&E Plan developed and collection of baseline data commenced* | On track |

## Activity Summary

The following activities were delivered and progress made during the reporting period. A full list of activities is located at ***Annex A:*** 24-month Schedule of Activities.

**Output 1: Regional Leadership -** The *1st* *Chief Justices’ Leadership Forum* (CJLF#1) took place in Port Moresby, Papua New Guinea (PNG) from 7-9 September. Twelve Pacific Island Countries (PICs) were represented. The purpose was for the PJSI management team to engage with the heads of partner courts to: introduce the Activity Design Document (ADD); plan activities for the coming 24-months; receive oversight, direction and feedback on activities and supply a forum for leadership dialogue and networking on judicial development. The meeting made several recommendations for consideration by the Initiative Executive Committee (IEC). Participants rated their satisfaction with the workshop at 91.67%. A link was established between PJSI partner courts and the New Zealand Judiciary with Judge Colin Doherty co-facilitating a session with Chief Justice Ingram on the International Framework for Court Excellence.

The *Initiative Executive Committee* (IEC) Meeting took place in Port Moresby, PNG on 10 September. The IEC was convened with members attending in person and through the use of remote technology. Members received a report on progress, provided strategic direction and considered the Chief Justice’s recommendations.

**Output 2: National Leadership** *-* Preparations for the *Project Management & Evaluation Workshop* are being finalised. The workshop will be held in Port Vila, Vanuatu from 20-24 February, 2017. The objective is to build capacity to produce desired results through the delivery of local development projects. Eighteen participants are registered to attend.

**Output 3: Leadership Incentive Fund (LIF)** *-* Guidelines and templates for the LIF were developed and submitted to MFAT on 25 August. The approved Guidelines were launched at the CJLF and the initial round of applications opened to 6 partner courts. Two applications have been received. The application from the Federated States of Micronesia (FSM) has been approved which will see the delivery of a Judicial Conference in February 2017. The application from Tokelau is being reviewed. Based on feedback from partner courts, the Guidelines have been streamlined. The opportunity to apply for LIF grants will be launched among all partner courts in the first half of 2017.

**Output 7: Institutionalising Professional Development** *-* Preliminary assessments for both sub-projects were completed, presented to and approved at the CJLF#1.

1. *Career Pathway Project*: the Institutionalising Professional Development Adviser visited Port Moresby, PNG from 31 October to 4 November. The Adviser assessed the capacity-building requirements of PNG Centre for Judicial Excellence (PCJE) to provide judicial education to the region. A detailed analysis of those needs along with a costed strategy and plan will be presented at the next leadership (CJLF#2) meeting to be held in Apia in early April.
2. *Career Gateway Project*: the Adviser visited Port Vila, Vanuatu from 29 January-4 February, 2017 to meet with representatives of the University of South Pacific (USP). Detailed discussions focused on introducing two entry-level regional programs comprising a Certificate and Diploma of Justice for lay adjudicators and court staff. A concept note including curriculum framework and courses will be presented at CLJF#2.

**Output 8: Human Rights** *-* A strategy and work plan were approved at the CJLF#1. The Human Rights Adviser has commenced drafting of a Toolkit for piloting and roll-out from mid-2017.

**Output 9: Gender & Family Violence -** A strategy and work plan were approved at the CJLF#1. Contracting of a local expert from within the Pacific was approved by MFAT and completed. The Gender & Family Violence (G&FV) Adviser and G&FV Local Expert have commenced drafting of a Toolkit for piloting and roll-out from mid-2017.

**Output 11: Accountability -** A strategy and work plan was developed and delivered to the CJLF in September 2016. The *Accountability Adviser* has begun implementing the work plan.The *Monitoring & Evaluation* (M&E) Plan is complete and is being implemented across processes and systems. Localisation of M&E practices will commence during the PM&E workshop. Collection of baseline data has commenced.

## Reach*[[1]](#footnote-1)*

Across the three activities delivered to-date, PJSI reached 22 judicial and court officers, 3 of whom (or 14%) were female.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Activity** | **Judicial Officers** | **Court Officers** | **Other**  **Roles** | **Total No. of Participants** |
| Chief Justices Meeting | 12 | - | - | 12 |
| Initiative Executive Committee Meeting | 4 | 1 | - | 5 |
| Career Pathway Project Local Visit #1 | 4 | 1 | - | 5 |
| ***TOTAL*** |  |  |  | ***22*** |

## Attributing Success

Successes during the reporting period can be attributed to quality processes executed efficiently relating to recruitment, mobilisation, activity design, stakeholder participation and ownership, scheduling and delivery.

## Primary Changes

Changes are not discernible at this early stage, as no capacity building/institutional strengthening activities have taken place during the mobilisation period. Six to twelve months following such activities it will be possible to begin considering changes. This period is required in order to allow learning to be applied, challenges to emerge and for resultant changes to become measurable. Changes will be measured by reference to indicators and against baseline and targets included in the Results Framework (***Annex B***).

## Risks and Opportunities

The risks identified in the ADD have been reviewed. They remain valid and current. Ongoing monitoring will identify and report on any emerging risks and opportunities.

## Refinements to PJSI Contracting or Approach

***Variation #1 - Allocation of an additional resource*:** Further to the recruitment process for the PJSI Gender and Family Violence Adviser, the PJSI team identified an opportunity to promote greater strategic benefits for our partner courts by recruiting a local expert from within the region: Mr. Tevita Seruilumi. The expert will provide technical, training and contextual support to the GFV Adviser. The Variation was approved by MFAT by email on 15 August.

***Approval of 3 additional activities:*** activity savings and contingency funding enabled two additional activities to be added to the implementation schedule. These comprise: a visit to FSM to improve Access to Justice; a visit to Tokelau related to improving Efficiency; and approval (subject to the availability of sufficient underspend from future activities) for a new Leadership Adviser role. These additional activities were approved by the IEC on 10 September.

***PJSI Leadership changes:*** changes in the membership of the IEC’s pacific membership and also with MFAT’s internal management team have required additional and support and facilitate the transition period. Additionally, due to the sad passing of Cook Islands Senior Justice of the Peace Mr. John Kenning, there is a need for MFAT and the region’s leadership to nominate a new lay-judiciary representative on the IEC.

## Capacity Improvements

During the mobilisation period and early in the implementation period, capacity building activities have not yet commenced. Capacity improvements may be discernible following several interventions. PJSI will therefore consider pre-PJSI capacity building activities to monitor and evaluate improvements six, 12 and additional months after an activity. This period is required in order to allow learning to be applied, challenges to emerge and for resultant changes to become measurable.

## Human Rights and Gender

Human rights and gender are integrated throughout PJSI’s design, processes and systems. In particular, the Gender & Family Violence Toolkit and the Human Rights Toolkit focus exclusively on issues to promote the treatment of related issues to improve gendered and human rights outcomes for people who use PIC courts.

## Sustainability

At this early stage it is not possible to comment on the sustainability of any of the activities. Sustainability is an integral design feature of all activities delivered. In this sense, the Toolkits are fundamentally an exercise in sustainability. Similarly, the Career and Pathways Projects aim to continue to build the professional capacity of PIC judiciaries through an in-region training provider, ameliorating the need for external intervention. This will be bolstered by the ongoing strengthening of capacity among the cadre of in-region trainers.

## Initiative Management

***Judicial Liaison Committee Meeting and Expressions of enterest form New Zealand and Australian Judicial Officers -*** Communication with both the New Zealand and Australian judiciaries continue through the Judicial Liaison Committee (JLC). A JLC meeting was held on 26 July. Discussions focused on confirming Committee membership; clarifying the role of the Committee; a progress report on mobilisation; and opportunities for, and ways to maximise involvement judicial and court from New Zealand and Australia. Numerous email exchanges have since taken place ensuring the Committee is abreast of all developments including circulation of documentation enabling judicial and court officers to express interest in participating in a number of activities. A total of 26 expressions of interest have now been received.

**Milestone Deliverables -** All agreed milestones were submitted on or before the date agreed:

|  |  |  |
| --- | --- | --- |
| **Milestone Report** | **Due** | **Submitted** |
| M. 1: Signed Arrangement between Recipient and MFAT. Submission of a claim. | 30 June, 2016 | **✓** |
| M. 2: Inception Period Completion Report, including Leadership Incentive Fund Guidelines, updated 24-month plan, and costed workplan | 31 August, 2016 | **✓** |
| **Milestone Report** | **Due** | **Submitted** |
| M. 3: Summary of progress report for the period date of signing the GFA to 31 January 2017 covering: outputs delivered to date; actual expenditure and income compared with that in the costed workplan, including comment on significant variances, balance of funds on hand as at 31 December 2016 | 15 February, 2017 | **✓** |

**Recruitment:** Recruitment processes commenced in July. Advisers were contracted for the following positions: Accountability Adviser, Human Rights Adviser, Gender & Family Violence Adviser, Access to Justice Adviser, Orientation Lead Adviser, Institutionalising Professional Development Adviser, Monitoring and Evaluation Adviser and a Project Management Adviser.

**Expenditure Summary:** Commercial – in confidence

**Counterpart communication:** The following communication with counterparts has taken place:

* *Newsletter****:*** the first PJSI newsletter was distributed to all partner courts and counterparts on 14 December. A copy is available <http://www.fedcourt.gov.au/pjsi/news>.
* *Website Statistics****:***The PJSI website was officially launched at the CJLF: [www.fedcourt.gov.au/PJSI](http://www.fedcourt.gov.au/PJSI). The website provides access to key documentation, as well as background and progress information on the Initiative. Between September and December the PJSI website recorded a total of 1,207 ‘page views’.[[2]](#footnote-2)

*Figure 1: Breakdown of total page views*

## Conclusion

The PJSI is now mobilised and activities are being delivered. Extensive preparations have been made across a range of activities in anticipation for a busy year of implementation in 2017. The PJSI Team is grateful for the direction and support of the region’s leadership in directing and guiding these activities. Without this high-level support, it would not be possible for the PJSI Team to implement the Initiative.

## Annexures

|  |  |  |
| --- | --- | --- |
| Annex A | - | 24-month Schedule of Activities |
| Annex B | - | Results Diagram & Framework |
| Annex C | - | Costed Workplan |
| Annex D | - | Expenditure Summary (to 31 December, 2016) |
|  | |  |  |

## Annex A: 24-month Schedule of Activities

**Pacific Judicial Strengthening Initiative**

**Activity Timing and Locations**

*as at 2 February, 2017*

***Regional Activities:***

| **Activity** | **Indicative Timing** | **Location** |
| --- | --- | --- |
| 1. ~~1~~~~st~~ ~~Chief Justices’ Leadership Forum~~ | ~~7-9 Sep, 2016~~ | ~~PNG~~ |
| 1. ~~1~~~~st~~ ~~Initiative Executive Committee Meeting~~ | ~~10 Sep, 2016~~ | ~~PNG~~ |
| 1. Project Management and Evaluation Workshop | 20-24 Feb, 2017 | Vanuatu |
| 1. 2nd Chief Justices’ Leadership Forum | 3-5 Apr, 2017 | Samoa |
| 1. 2nd Initiative Executive Committee Meeting | 6-7 Apr, 2017 | Samoa |
| 1. Regional Certificate-level Training-of-Trainers Workshop | 12-23 Jun, 2017 | Cook Islands |
| 1. Leadership Workshop   (Topic: *Leadership & Human Rights*, TBC) | 5-7 Sep, 2017 | Tonga |
| 1. 3nd Initiative Executive Committee Meeting | 25 Sep, 2017 | Remote |
| 1. Regional Lay Judicial Officer Orientation Workshop | 20-24 Nov, 2017 | Solomon Is. |
| 1. Substantive / Capacity Development Training-of-Trainers Workshop (Topic: *Access to Justice & Human Rights*, TBC) | 12-16 Feb, 2018 | Vanuatu |
| 1. 3rd Chief Justices’ Leadership Forum | 16-18 Apr, 2018 | Auckland |
| 1. 4th Initiative Executive Committee Meeting | 19-20 Apr, 2018 | Auckland |

***Leadership Incentive Fund Activities:***

| **Activity** | **Deadlines** |
| --- | --- |
| *LIF Applications available for all PICs*  *(depending on availability of funds - assessed on a ‘first-in-first served’ basis)* | 30 September;  30 March; 30 June |

***In-PIC Local Activities:***

| **Activity** | **Tentative Timing** | **Location** |
| --- | --- | --- |
| ***National Leadership Output*** *(all inputs aligned with Large-scale LIF grants)* | | |
| 1. Local Project Management and Planning Visit #1 | TBC | TBC |
| 2. Local Project Management and Planning Visit #2 | TBC | TBC |
| 3. Local Project Management and Planning Visit #3 | TBC | TBC |
| 4. Local Project Management and Planning Visit #4 | TBC | TBC |
| ***Access to Justice Output*** *(Enabling Rights)* | |  |
| 1. 1. Local Visit #1 | 15-26 May, 2017 | FSM |
| 2. Local Visit #2 | 5-16 Mar, 2018 | Marshall Islands |
| ***Professional Development Output*** |  |  |
| 1. Local Orientation Visit #1 | 19-28 Jul, 2017 | Tuvalu |
| 2. Local Orientation Visit #2 | 6-17 Aug, 2017 | Marshall Islands |
| 3. Local Orientation Visit #3 | 9-18 May, 2018 | Samoa |
| 4. Local Orientation Visit #4 | 11-20 Jul, 2018 | Solomon Islands |
| ***Human Rights Output*** |  |  |
| 1. Piloting of HR resource / toolkit | 24 Apr-5 May, 2017 | Solomon Islands |
| 2. Local Visit #1 | Nov, 2017 | PNG |
| 3. Local Visit #2 | 23 Apr-4 May, 2018 | Kiribati |
| ***Gender and Family Violence Output*** |  |  |
| 1. Piloting of GFV resource / toolkit | 17-28 April, 2017 | Tonga |
| 2. Local Visit #1 | 16-27 Oct, 2017 | Nauru |
| 3. Local Visit #2 | 19 Feb-2 Mar, 2018 | Cook Islands |
| 4. Local Visit #3 | 16-27 Jul, 2018 | Vanuatu |
| ***Efficiency Output*** |  |  |
| 1. Local Visit #1 | 9-20 Oct, 2017 | Palau |
| 2. Local Visit #2 | 11-22 Jun, 2018 | Niue |

***In-PIC / remote regional activities:***

| **Activity** | **Tentative Timing** | **Location** |
| --- | --- | --- |
| ***National Leadership Output*** | |  |
| 1. Remote Delivery Facilitation #1 | Sept 2016-May 2017 | Remote / Regional |
| 2. Remote Delivery Facilitation #2 | Jun 2017-May 2018 | Remote / Regional |
| ***Localising Professional Capacity Building Output*** | |  |
| 1. Mentoring / resource sharing with local trainers | Sept 2016-May 2017 | Remote / Regional |
| 2. Mentoring / resource sharing with local trainers | Jun 2017-May 2018 | Remote / Regional |
| ***Institutionalising Professional Development Output*** | | |
| ~~1. Career Gateway: Local Visit #1~~ | ~~30 Jan-3 Feb 2017~~ | ~~Vanuatu~~ |
| 2. Career Gateway: Local Visit #2 | TBC | TBC |
| 3. Career Gateway: Local Visit #3 | TBC | TBC |
| ~~4. Career Pathway: Local Visit #1~~ | ~~31 Oct-4 Nov 2016~~ | ~~PNG~~ |
| 5. Career Pathway: Local Visit #2 | TBC | TBC |
| ***Accountability Output*** |  |  |
| 1. Collection, analysis & publication of court performance data | TBC | Remote |
| 2. Expand collection of data | TBC | Remote |
| 3. Court User Perception Surveys | TBC | Remote |
| 4. Data Management: collection, collation, analysis & reporting (IFCE Adviser) | TBC | Remote |
| ***Accountability Output*** |  |  |
| 1. M&E Assistance Local Visit #1 | 27 Mar-7 Apr, 2017 | Samoa |
| 2. M&E Assistance Local Visit #2 | 16-27 Apr, 2018 | Auckland |

## Annex B: Results Diagram and Framework

***Short-term Outcomes***

***Medium-term Outcomes***

***Long-term Outcomes***

***Key Short-Term Outputs***

**Goal: Building fairer societies through fair, responsive, efficient and accessible justice.**

**STO 1.1.1:** Improved capacity of *judicial leadership* to assess needs, plan, own & lead judicial development locally.

**STO 2.1.2:** PICSSSs operate with a higher level of *professionalism*

**LTO 1.0: Leadership:** Judicial leaders are leading and managing change locally.

**LTO 2.0: Performance:** Court services are more accessible, just, efficient & fair ffairresponsive.

**STO 2.1.3:** PICSSSs exhibit more responsive & just behaviour & treatment that is fair & reasonable (*substantive justice)*.

**STO 2.1.4:** Cases are disposed of more efficiently (*procedural justice).*

**STO 2.1.1:** Marginalised & vulnerable groups better able to *access justice* in and through courts.

**MTO 1.1:** Increased capacity & progress towards leading & managing change locally.

**MTO 2.1:** Court services are more accessible, just, efficient and responsive.

***Key Output 1:*** ***Regional Leadership:*** Chief Justices trained in leadership & associated tools provided.

***Key Output 5:*** ***Professional Development:*** Judicial /

Court Officers trained in priority areas of knowledge skill & attitude.

***Key Output 2:* *National Leadership:***National judicial leaders trained in leadership & change management & associated tools provided.

***Key Output 4:*** ***Access to Justice:***

PICSSS courts committed to improving access to justice, people trained & relevant tools provided.

***Key Output 3: Leadership Incentive Fund:***

Local activities conducted through training & funding provided.

***Key Output 6:*** ***Localising Professional Capacity Building:*** PICSSSs trained and equipped with resources to address needs locally.

***Key Output 7: Institutionali-sing Professional Development***:

A modality to institutionalise cost-effective / sustainable in-region training.

***Key Output 8:*** ***Human Rights:***

PICSSS courts committed, trained & equipped with tools to deliver justice aligning with human rights.

***Key Output 9:*** ***Gender & Family Violence:***

PICSSSs committed, trained & equipped with tools to better respond to gender & family violence issues.

***Key Output 10:*** ***Efficiency:***

PICSSS courts trained & equipped with the tools & capacity to improve efficiency in the administration of justice.

***Key Output 11:***  ***Accountability:*** Court performance monitored, evaluated & reported on to improve accountability

**Improved judicial systems across the Pacific.**

***MFAT Programme Outcome***

| **Aim[[3]](#footnote-3)** | | **Indicators** | **Baseline** | **Target[[4]](#footnote-4)** | **Methodology & Data Source** | **DAC** |
| --- | --- | --- | --- | --- | --- | --- |
| Goal | Building fairer societies through more accessible, just, efficient and responsive court services. | % of public trust and confidence in partner courts[[5]](#footnote-5) | 73% of court users[[6]](#footnote-6) are satisfied with, trust and respect the courts.[[7]](#footnote-7) | 15% increase in public trust and confidence | Court user perception survey conducted by partner courts, supported by FCA. | Impact |
| Improvement in rankings in World Bank’s Governance Indicators (Rule of Law & Voice and Accountability) | *Moderate* (Samoa, Tuvalu, Palau and Vanuatu) to *precarious* in all other PICs*.* | Improvement in overall score | WGI Annual Reports. | Impact |
| Long-term outcome (YR5) | 1: Judicial leaders are leading and managing change locally | The extent to which change is driven locally[[8]](#footnote-8) | On average, 63% of change is driven locally[[9]](#footnote-9) | 20-50% increase in locally driven change[[10]](#footnote-10) | PICs & MEA assessment against defined measures. | Sustainability |
| 2: Court services are more accessible, just, efficient and responsive. | % of court users who are satisfied with courts or consider them accessible, just, efficient and responsive | To be supplied by the end of year 1 | 20-50% increase in court users’ satisfaction | Court user perception survey conducted by partner courts in concert with FCA | Relevance |
| Number of people trained/supported to strengthen PICs courts[[11]](#footnote-11) | 22 people have been trained / supported to date | 1,139 people trained / supported, 30% of whom are women (YR5: 153, YR4: 203, YR3: 271,YR2: 276, YR1: 236) | Collated figures from all PJSI and local training / advisory activities. | Effectiveness |
| Medium-term outcome (YR3-4) | 1.1 Increased capacity & progress towards leading / managing change locally | Extent to which change is driven locally [[12]](#footnote-12) | On average, 63% of change is driven locally[[13]](#footnote-13) | 15-40% increase in locally driven change[[14]](#footnote-14) (YR 3: 3-20% increase) | PICs & MEA assessment against defined measures. | Sustainability |
| * 1. Court services are more accessible, just, efficient and responsive |  | To be supplied by the end of year 1 | 15 - 30% increase in understanding/confidence (YR3: 5-15%)[[15]](#footnote-15) | Court user perception survey conducted by partner courts in concert with FCA | Effectiveness |
|  | On average, 67% of officers deliver excellent service[[16]](#footnote-16) | 15-40% increase in excellent service (YR3: 10-30%)[[17]](#footnote-17) | Self-assessment against action plans[[18]](#footnote-18) |  |
| Extent to which court users consider that PIC courts exhibit responsive and just behaviour and treat people fairly and reasonably. | On average 74% of results delivered are considered fair [[19]](#footnote-19) | 15-40% improvement in delivering fairer results (YR3: 10-30%)[[20]](#footnote-20) | Court user perception survey conducted by partner courts in concert with FCA | Relevance |
| Number of backlogged / delayed cases in partner courts (*procedural justice*) | 16% of respondents to the PJSI TNA cited delay as the most significant need.[[21]](#footnote-21) PICs courts collect insufficient data to evaluate ability to provide remedies. | 20%-30% decrease in case backlog and delay (YR3: 10-20%)[[22]](#footnote-22) | PICs case management records | Efficiency |
| Short-term outcomes (YR1-2) | 1.1.1 Improved capacity of *judicial leadership* to assess needs, plan, own and lead judicial development locally. | Extent to which change is driven locally [[23]](#footnote-23) | On average, 63% of change is driven locally | 5-20% increase in locally driven changes (YR1: 0-10% focus will be on building awareness / capacity) | PICs & MEA assessment against defined measures. | Sustainability |
| 2.1.1 Marginalised and vulnerable groups better able to *access justice* in and through courts. | The extent to which the needy understand, and are confident to exercise their rights. | To be supplied by the end of year 1 | 5 - 10% increase in understanding / confidence (YR1: 0-5% focus will be on building internal awareness / capacity) | Court User perception survey | Relevance |
| 2.1.2 Partner courts operate with a higher level of *professionalism* | Extent to which officers deliver excellent service | 77% of court users report some or significant improvement in the conduct and professionalism of judicial and court officers.[[24]](#footnote-24) | 5-20% increase in professionalism (YR1: 0-10% focus will be on building awareness / capacity) | Post-training satisfaction/learning surveys (completed by pax/TA) & learning application surveys completed 6 & 12 months after the training (completed by pax/CJ/Registrar or nominee). | Effectiveness |
| 2.1.3 Partner courts exhibit more responsive & just behaviour & treatment that is fair & reasonable (*substantive justice)*. | Extent to which courts deliver fair results | On average 74% of results delivered are considered fair | 5-10% improvement in delivering fairer results (YR1: 0-5% focus will be on building internal awareness / capacity) | PICs/TA documented assessment of relevant reforms | Impact |
| 2.1.4 Cases are disposed of more efficiently (*procedural justice).* | Number of backlogged / delayed cases backlog in partner courts | 16% of respondents to the PJSI TNA cited delay as the most significant need.[[25]](#footnote-25) PICs courts collect insufficient data to evaluate ability to provide remedies. | NA (no activities planned for the first two years) | PICs case management records | Efficiency |
| Outputs | 1 Regional Leadership - Chief Justices trained in leadership & associated tools provided. | The number of:   * people trained / supported in leadership * people satisfied with training / support * inter-courts links established | NA | * 2 x regional activities in years 1-4 and 1 x regional activity in year 5 each attended by 14 pax (=14 pax) * 80% satisfaction rating * 5 inter-court links established | FCA/TA reports |  |
| 2 - National Leadership - National judicial leaders trained in leadership & change management & associated tools provided. | The number of:   * people trained / supported in change management * people satisfied with the training / support | NA | * 1 x regional activity attended by 14 pax (= 14 pax) * 8 x local activities each training / supporting x 10 pax (=80pax) * 5 x remote activities each training / supporting x 5 pax (=5 pax) * 80% mean satisfaction rating | FCA/TA reports & PICs reports |  |
| 3 - Leadership Incentive Fund -Local activities conducted through training & funding provided. | The number of grants awarded and activities implemented | NA | * Equitable portion of 35 grants provided over 5 years * All activities implemented | FCA records & PICs grant reports |  |
| 4 - Access to Justice - PICs courts committed to improving access to justice, people trained & relevant tools provided. | Number of:   * people trained / supported * people satisfied with training / support * local resources developed and used/delivered | NA | * 1 x regional activity attended by 14 pax (=14 pax) * 4 x local activities each training / supporting x 10 pax (=40 pax) * 80% mean satisfaction rating | FCA/TA reports & PICs reports |  |
| 5 - Professional Development - Judicial / Court Officers trained in priority areas of knowledge skill & attitude. | Number of:   * people trained * people satisfied with training * local resources developed and used/delivered | NA | * 5 x regional activity attended by 14 pax (=70 pax) * 4 x local activities each training / supporting x 10 pax (=40 pax) * 80% mean satisfaction rating | FCA/TA reports |  |
| 6 - Localising Professional Capacity Building - PICs judicial / court officers trained to address needs locally. | Number of:   * people trained / supported * people satisfied with training / support * local resources developed and used/delivered | NA | * 3 x regional activity attended by 14 pax (=42 pax) * 5 x remote activities each training / supporting x 5 pax (=25 pax) * 80% mean satisfaction rating | FCA/TA reports & PICs activity reports |  |
| 7 - Institutionalising Professional Development - A modality to institutionalise cost-effective / sustainable in-region training. | * Options paper completed * Inter-agency linkages established / operating | NA | * 2 x regional activities supporting x 10 pax (=20 pax) * 80% mean satisfaction rating | Options paper & FCA/TA reports |  |
| 8 - Human Rights - PICs courts committed, trained & equipped with tools to deliver justice aligning with human rights. | Number of:   * people trained / supported * people satisfied with training / support * local resources developed and used/delivered * NGO/CBO linkages established | NA | * 2 x regional activity attended by 14 pax (=28 pax) * 4 x local activities each training / supporting x 10 pax (=40 pax) * 80% mean satisfaction rating | FCA/TA reports & PICs activity reports |  |
| 9 - Gender & Family Violence - PICs courts committed, trained & equipped with tools to better respond to gender & family violence issues. | Number of:   * people trained / supported * people satisfied with training / support * local resources developed and used/delivered * NGO/CBO linkages established | NA | * 2 x regional activity attended by 14 pax (=28 pax) * 5 x local activities each training / supporting x 10 pax (=50 pax) * 80% mean satisfaction rating | FCA/TA reports & PICs activity reports |  |
| 10 - Efficiency - PICs courts equipped with the tools and capacity to improve efficiency in the administration of justice. | * New toolkit developed * Number of people trained to implement the toolkit * Number of PICs implementing new policies, standards, systems, processes to improve administration | NA | * 5 x local activities each training / supporting x 10 pax (=50 pax) * 80% mean satisfaction rating | FCA/TA reports & PICs activity reports |  |
| 11 - Accountability - Court performance monitored, evaluated & reported on to improve accountability. | Number of PICs:   * routinely producing annual reports * developing systems / methodologies to expand data collection * collecting IFCE, gender & GFV compliant disaggregated data | NA | * 5 x regional activity attended by 14 pax (=70 pax) * 5 x local activities each training / supporting x 10 pax (=50 pax) * 15 days remote, training/supporting x 5 pax (=5 pax) * 80% mean satisfaction rating | FCA/TA reports & PICs activity reports |  |

**Analysis of Progress against Outputs**

|  |  |  |  |
| --- | --- | --- | --- |
| **Output / Aim** | **Indicator** | **Target** | **Analysis** |
| 1 Regional Leadership - Chief Justices trained in leadership & associated tools provided. | The number of:   * people trained / supported in leadership * people satisfied with training / support * inter-courts links established | * 2 x regional activities in years 1-4 and 1 x regional activity in year 5 each attended by 14 pax (=14 pax) * 80% satisfaction rating * 5 inter-court links established | * 12 PICs were represented at the first Chief Justices’ Leadership Forum. * 92% were satisfied with the meeting * No inter-court links were established. |
| 2 - National Leadership - National judicial leaders trained in leadership & change management & associated tools provided. | The number of:   * people trained / supported in change management * people satisfied with the training / support | * 1 x regional activity attended by 14 pax (= 14 pax) * 8 x local activities each training / supporting x 10 pax (=80pax) * 5 x remote activities each training / supporting x 5 pax (=5 pax) * 80% mean satisfaction rating | * No activities conducted. * Planning and preparations for the Project Management and Evaluation Workshop are underway. |
| 3 - Leadership Incentive Fund -Local activities conducted through training & funding provided. | The number of grants awarded and activities implemented | * Equitable portion of 35 grants provided over 5 years * All activities implemented | * Fund launched, 2 applications received. 1 approved, 1 being review. |
| 4 - Access to Justice - PICs courts committed to improving access to justice, people trained & relevant tools provided. | Number of:   * people trained / supported * people satisfied with training / support * local resources developed and used/delivered | * 1 x regional activity attended by 14 pax (=14 pax) * 4 x local activities each training / supporting x 10 pax (=40 pax) * 80% mean satisfaction rating | * No activities conducted. |
| 5 - Professional Development - Judicial / Court Officers trained in priority areas of knowledge skill & attitude. | Number of:   * people trained * people satisfied with training * local resources developed and used/delivered | * 5 x regional activity attended by 14 pax (=70 pax) * 4 x local activities each training / supporting x 10 pax (=40 pax) * 80% mean satisfaction rating | * No activities conducted. |
| 6 - Localising Professional Capacity Building - PICs judicial / court officers trained to address needs locally. | Number of:   * people trained / supported * people satisfied with training / support * local resources developed and used/delivered | * 3 x regional activity attended by 14 pax (=42 pax) * 5 x remote activities each training / supporting x 5 pax (=25 pax) * 80% mean satisfaction rating | * No activities conducted. |
| 7 - Institutionalising Professional Development - A modality to institutionalise cost-effective / sustainable in-region training. | * Options paper completed * Inter-agency linkages established / operating | * 2 x regional activities supporting x 10 pax (=20 pax) * 80% mean satisfaction rating | * Preliminary assessments of Career Gateway and Pathway components completed. |
| 8 - Human Rights - PICs courts committed, trained & equipped with tools to deliver justice aligning with human rights. | Number of:   * people trained / supported * people satisfied with training / support * local resources developed and used/delivered * NGO/CBO linkages established | * 2 x regional activity attended by 14 pax (=28 pax) * 4 x local activities each training / supporting x 10 pax (=40 pax) * 80% mean satisfaction rating | * Strategy approved and Toolkit drafting commenced. |
| 9 - Gender & Family Violence - PICs courts committed, trained & equipped with tools to better respond to gender & family violence issues. | Number of:   * people trained / supported * people satisfied with training / support * local resources developed and used/delivered * NGO/CBO linkages established | * 2 x regional activity attended by 14 pax (=28 pax) * 5 x local activities each training / supporting x 10 pax (=50 pax) * 80% mean satisfaction rating | * Strategy approved and Toolkit drafting commenced. |
| 10 - Efficiency - PICs courts equipped with the tools and capacity to improve efficiency in the administration of justice. | * New toolkit developed * Number of people trained to implement the toolkit * Number of PICs implementing new policies, standards, systems, processes to improve administration | * 5 x local activities each training / supporting x 10 pax (=50 pax) * 80% mean satisfaction rating | * No activities conducted. |
| 11 - Accountability - Court performance monitored, evaluated & reported on to improve accountability. | Number of PICs:   * routinely producing annual reports * developing systems / methodologies to expand data collection * collecting IFCE, gender & GFV compliant disaggregated data | * 5 x regional activity attended by 14 pax (=70 pax) * 5 x local activities each training / supporting x 10 pax (=50 pax) * 15 days remote, training/supporting x 5 pax (=5 pax) * 80% mean satisfaction rating | * Strategy approved and work commenced. * M&E Plan developed and implemented across PJSI systems/processes, localisation to commence during PM&E workshop. |

## Annex C: Expenditure Summary (to 31 December, 2016)

[Commercial – in confidence

## Annex D: Costed Workplan

Submitted to MFAT separately

1. Reach refers directly to the total number of activities delivered in the reporting period, audience size and audience makeup; and indirectly to groups who receive flow-on benefit. [↑](#footnote-ref-1)
2. Note: the ‘Total Page Views’ statistic counts multiple visit to the one page by the same user. [↑](#footnote-ref-2)
3. The term ‘Aim’ is provided by MFAT, but refers to ‘Outcomes’ as defined in the Results Diagram. [↑](#footnote-ref-3)
4. The FCA will revisit all targets at the first regional leadership meeting to ensure all Chief Justices are aligned with them. The FCA would like to establish more ambitious targets if MFAT is able to provide an incentive for it to do so. [↑](#footnote-ref-4)
5. MFAT’s strategic Results Framework Indicators – Law and Justice, supplementary indicator. [↑](#footnote-ref-5)
6. Court users are those who use the courts to assert/protect their legal rights. Court actors are those who perform functions within the courts such as judicial and court officers. [↑](#footnote-ref-6)
7. This baseline is aggregated over all PICSSSs. Some PICSSSs provided a number of responses, others few. The representativeness of the data is not sufficiently strong to provide high, medium and low capacity PICSSS baseline. [↑](#footnote-ref-7)
8. Indicative measures include; existence and active operation of National Judicial Development Committees (however named), existence and active implementation of local strategic development plans (however named), number of local trainers and the extent to which they are encouraged/able to conduct training, number of local training/development activities conducted, number of locally inspired/led changes implemented, capacity to assess needs, design, implement, monitor and evaluate local activities. Success is measured by internal assessment of the following 5 OECD-DAC: 1) Did the project address the identified need? [relevance & effectiveness] 2) Did it demonstrably achieve its stated objective/s and (overtime) deliver its intended result/s? [impact] 2) Was it delivered on time and within budget? [efficiency] 3) Will the outcomes and results live on over time? [sustainability]. [↑](#footnote-ref-8)
9. Refer to Table 1 in PICSSS self-assessment for baselines indicated by PICSSS representatives at the Activity Design Consultation Workshop (Auckland 23-24 February, 2016). [↑](#footnote-ref-9)
10. As above. [↑](#footnote-ref-10)
11. MFAT’s Strategic Results Framework Indicators – Law and Justice, indicator 8.1D. This data will comprise in-person days, the number of people successfully completing the training both provided by PJSI and locally by partner courts (where the latter data is available), gender-disaggregating and distinguishing the types of court actors (eg judicial and court officers). The figures will be presented as a percentage of total population. This also addresses MFAT Strategic Results Framework Indicators – supplementary indicators. [↑](#footnote-ref-11)
12. Indicative measures include; the existence and active operation of National Judicial Development Committees (however named), the existence and active implementation of local strategic development plans (however named), number of local trainers and the extent to which they are encouraged/able to conduct training, the number of local training/development activities conducted, the number of locally inspired/led changes underway, implemented and embedded, capacity to assess needs, design, implement, monitor and evaluate local activities. Success is measured by internal assessment of the following 5 OECD-DAC: 1) Did the project address the identified need? [relevance] 2) Did it demonstrably achieve its stated objective/s [effectiveness ] and overtime, deliver its intended result/s? [impact] 2) Was it delivered on time and within budget? [efficiency] 3) Will the outcomes and results live on over time? [sustainability]. [↑](#footnote-ref-12)
13. Refer to Table 1 in PICSSS self-assessment for baselines indicated by PICSSS representatives at the Activity Design Consultation Workshop (Auckland 23-24 February, 2016). [↑](#footnote-ref-13)
14. Ibid. [↑](#footnote-ref-14)
15. Ibid, refer to Table 3. [↑](#footnote-ref-15)
16. Ibid, refer to Table 2. [↑](#footnote-ref-16)
17. Ibid. [↑](#footnote-ref-17)
18. Action plans will be developed during all training activities and used to assess incremental improvement over time. [↑](#footnote-ref-18)
19. Refer to Table 4 in PICSSS self-assessment for baselines indicated by PICSSS representatives at the Activity Design Consultation Workshop (Auckland 23-24 February, 2016) [↑](#footnote-ref-19)
20. Ibid. [↑](#footnote-ref-20)
21. Pacific Judicial Strengthening Initiative, *Needs Assessment Report and Indicative Design Concept,* 2016, Sydney, p 6. [↑](#footnote-ref-21)
22. Ibid. [↑](#footnote-ref-22)
23. Indicative measures include; the existence and active operation of National Judicial Development Committees (however named), the existence and active implementation of local strategic development plans (however named), number of local trainers and the extent to which they are encouraged/able to conduct training, the number of local training/development activities conducted, the number of locally inspired/led changes underway, implemented and embedded, capacity to assess needs, design, implement, monitor and evaluate local activities. Success is measured by internal assessment of the following 5 OECD-DAC: 1) Did the project address the identified need? [relevance] 2) Did it demonstrably achieve its stated objective/s [effectiveness ] and overtime, deliver its intended result/s? [impact] 2) Was it delivered on time and within budget? [efficiency] 3) Will the outcomes and results live on over time? [sustainability]. [↑](#footnote-ref-23)
24. Pacific Judicial Development Programme. Federal Court of Australia. *Completion Report 2010 – 2015,* Sydney,2015, A-59. [↑](#footnote-ref-24)
25. Pacific Judicial Strengthening Initiative, *Needs Assessment Report and Indicative Design Concept,* 2016, Sydney, p 6. [↑](#footnote-ref-25)